## INDEX & Instructions
INDEX - SAFETY IN DESIGN REPORT
1 | Executive Risk Summary
2 | Approvals & Revision History |  | go to top
3 | Risk Register
Water Corporation Risk Assessment Criteria
Water Corporation Guidewords
`
Scroll up or click here to get to the top of this page
Note on D10: OSH Regulations 1996 - 3.140 - Designer of work for commercial client to give client report In accordance with these regulations designers must provide their clients with a written report on the OSH aspects of their designs. This report should set out: • The hazards – o That the designer has identified as part of the design process; o That arise from the design of the end product of the construction work; and o To which a person at the construction site is likely to be exposed. • The designer’s assessment of the risk of injury or harm to a person resulting from those hazards; • What things the designer has done to reduce those risks (for example, changes to the design, changes to construction methods); and • Which of those hazards the designer has not done anything in respect of to reduce those risks. Dangerous Good's Safety (Storage and Handling of Non Explosives) Regulations 2007 Impose additional requirements on designers to identify and manage risk. The Water Corporation has integrated these requirements in to the Safety in Design process through the inclusion of appropriate keywords and the required involvement of suitably experienced personnel. OSH Act 1984 Section 23 States that the designers and suppliers of plant have to ensure that all operational and maintenance hazards have been identified and controlled as far as reasonable practicable and that any information about these hazards should be provided to the operators of the plant.
Confidentiality Notice
Access to this document and referenced documents is provided to the recipient under the following conditions:
- The contents are to be used solely for the purposes of Corporation work
- The document will not be made accessible to any external party other than (if necessary) contractors currently engaged by the Corporation under a contract which addresses confidentiality
- Any requirement to vary these conditions is to be referred to the Head of Engineering.
© Copyright Water Corporation 2013-2018
Except as provided by the Copyright Act 1968, no part of this document may be reproduced, stored in a retrieval system or transmitted in any form or by any means without the prior written permission of the Corporation. Enquiries should be directed to the Head of Engineering.
Introduction
The Safety in Design (SiD) process as required by relevant OSH ACT and Regulations is the integration of hazard identification and risk assessment methods as early as possible in the planning and design process to eliminate or bring the risks of injury to ‘As Low As is Reasonably Practicable’ (ALARP) throughout the life of the asset or process being designed. A safe design approach considers the safety of those who design, construct, maintain, clean, repair and demolish an asset as well as those who work in or with it.
This Safety in Design Report ("SiD Report") is prepared by the Designer and satisfies obligations and responsibilities set out in relevant Regulation in respect of the designer’s scope of work.
The SiD Report includes safety and other risks that are introduced by the specific design approach for the designer's scope of work, and is considerate of operability,and constructability risks. The report is devided in 3 sections:, which all form part of the deliverables that are submitted to the Water Corporation as part of the design.
1. Executive summary
2. Approvals and revision history
3. Risk Register
Objective
The objective of the SiD Report is to articulate and communicate all hazards and risks associated with the design, and in turn treat those hazards to ensure - so far as is reasonably practicable - the safety of workers and the general public by using the highest reasonable risk treatment (hierarchy of control).
Safe design is the Designer’s responsibility. As the design progresses the Designer captures hazards and risks identified and records decisions relating to their risk treatment in a Risk Register (sheet 3) This Register is carried through and updated in each phase of the design and forms the Report.
At the start of construction, at the start-up meeting, the Designer will present relevant points form the Safety in Design Report to the Contractor - and specifically the Executive Risk Summary (sheet 1) to the Constructor. A Safety in Design presentation should be prepared to explain the context for preparing the SiD Report, the benefits of the report for constructors, the high or extreme risks that have been mitigated or not through the design and what actions are suggested for the constructor to manage these risks. The Project Manager and Superintendents Representative will work with the Constructor to action the proposed controls during the life of the project.
The Designer must maintain the Risk register in this SiD Report and the risk treatment strategies for each identified risk. See "Management of Change" below for further instructions.
Management of change
This SiD Report will be based on information available and accumulated during the design process, the existing site conditions, the location of existing services and infrastructure.
Any modification to the design during the construction stage or maintenance stage could vary the risks initially assessed and in such case the SiD Report should be reviewed to determine whether the changes alter any risks or create any new risks and whether additional risk treatment is required. The Risk Register, Executive Summary and the Approvals and Revision History in the Report should be updated to reflect the change.
Should any changes to the design of an asset be considered during construction, then the Project Manager or Contract Manager must consult the Design Manager to ascertain whether the change has an impact on the residual safety risk. If the Design Manager determines that change may alter the SiD Report they must consult with the Designer and Project Manager to update the SiD Report and communicate the changes to the Contractor such that all risks are brought to a level considered to be SFAIRP again. Any change is reflected in the Risk Register, Executive Summary and recorded in the Approval and Revision history worksheets. Notification of change to residual risks that are relevant to construction activities will need to be provided to the Construction Manager.

## 1. EXEC RISK SUMMARY
Safety in Design Report - SUMMARY
C00000 - Water Corporation SAP Project Number & title
Date
SCOPE OF WORK
SUMMARY OF RISKS
Risk Register Summary
STATUS OF RISK SUMMARY |  | OPEN INITIAL RISK SUMMARY |  | RISK TREATMENT SUMMARY |  | OPEN RESIDUAL RISK SUMMARY
# of open risks | 4 | # of Extreme initial risks | 0 | # not treated | 0 | # of Extreme residual risks | 0
# of closed risks | 0 | # of High initial risks | 4 | # PPE treatment | 0 | # of High residual risks | 0
|  | # of Moderate initial risks | 0 | # Administrative treatment | 1 | # of Moderate residual risks | 3
|  | # of Low initial risks | 0 | # Engineering treatment | 2 | # of Low residual risks | 1
|  |  |  | # Substitution treatment | 0
|  |  |  | # Isolation treatment | 1
|  |  |  | # Elimination treatment | 0
go to top
EXECUTIVE SUMMARY
Provide a short summary of the scope of work to set the context of this SiD Report and associated risk assessment.

## 2. Approval & Revision history
Safety in Design Report - APPROVALS & REVISIONS
C00000 - Water Corporation SAP Project Number & title
Date
Document Preparation and Approval
INSTRUCTIONS
| Prepared By: | ________________________(signature) | Date: | ______________ |  | To be signed by the Designer undertaking the preparation of the Safety in Design report (eg. consultant's Job Manager, contractor's designer or Water Corporation's Design Manager for in-house design).
Name:
| Position: | Designer
| Organisation: | ___________________
| Approved By: | ________________________(signature) | Date: | ______________ |  | To be signed the designer's supervisor or the Water Corporation's Design Team Leader for in-house design.
| Name: | ___________________
| Position: | Reviewer
| Organisation: | ___________________
| Hand-over to Contractor | ________________________(signature) | Date: ______________ |  |  | The Project Manager shall invite the Designer to project kick-off meeting or organise a meeting with the Contractor at a suitable time prior to the commencement of construction to explain the risks and hazards related to the project
| Name: | ___________________
| Position: | Construction Manager
| Organisation: | ___________________
| TABLE OF REVISIONS |  |  |  |  | INSTRUCTIONS
| Date | Description of risk impact and change (incl. Risk Register risk ref #) | Prepared By | Approved By | Construction notice of change | Any modification to the design during the construction or maintenance stage could vary the risks initially assessed and in such case the SiD Report should be reviewed to determine whether the changes alter any risks or create any new risks and whether additional risk treatment is required. The Risk Register, Executive Summary and the Approvals and Revision History in the Report should be updated to reflect the change. Should any changes to the design of an asset be considered during construction, then the Project Manager or Contract Manager must consult the Design Manager to ascertain whether the change has an impact on the residual safety risk. If the Design Manager determines that change may alter the SiD Report they must consult with the Designer and Project Manager to update the SiD Report and communicate the changes to the Contractor such that all risks are brought to a level considered to be SFAIRP again. Any change is reflected in the Risk Register, Executive Summary and recorded in the Approval and Revision history worksheets. Notification of change to residual risks that are relevant to construction activities will need to be provided to the Construction Manager.
| 2022-07-19 | Minor update to Risk Treatment Description in both Safety in Design Risk Register and Safety in Planning Risk Register | Alistair Fleming | Michael Somerford
| 2024-01-22 | Scheduled review no changes required | Michael Somerford | Michael Somerford

## 3. SiD RISK REGISTER
Safety in Design Report - RISK REGISTER | [10 empty] | # not treated | 0 | # Substitution | 0
C00000 - Water Corporation SAP Project Number & title | [5 empty] | # of open risks | 4 |  |  |  | # PPE | 0 | # Isolation | 1
Date | [5 empty] | # of closed risks | 0 |  |  |  | # Administrative | 1 | # Elimination | 0
[11 empty] | # Engineering | 2
|  |  | 1. Hazard Identification |  |  | 2. Initial (Uncontrolled) Risk Assessment |  |  |  |  | 3. Risk Treatment |  |  |  | 4. Residual Risk Assessment
Date Entered/ Updated | Risk Status | Ref | Asset Life cycle Stage | Hazard Guideword | Hazard Description | Consequence Description | Consequence severity rating | Likelihood rating | Retained Risk | Risk level | Treatment Control Type | Action Description | Why Higher Treatment Control not Adopted? | Action Assignee | Consequence severity rating | Likelihood rating | Risk level
The latest revision date should be included here | Closed Risk Status applies to hazards that have no residual risk (i.e. the hazard has been eliminated for the relevant lifecycle stage), or the lifecycle is complete so the risk is no longer relevant (i.e. design is complete so risks in the Design Life Cycle Stage are now Closed) | # | When will the hazard be encountered? (not necessarily when the hazard will be treated) | Guidewords are used to help identify hazards. Refer to 'Water Corporation Guidewords' tab | What is the potential source of harm? | What could happen and who could be affected? | Refer to Consequence rating table under 'Risk Assessment Criteria' tab | Refer to Likelihood rating table under 'Risk Assessment Criteria' tab |  | Refer to Risk Matrix under 'Risk Assessment Criteria' tab | Using the control hierarchy, the highest practical control should be implemented, or listed as a recommendation for others | What has been done to reduce the risk so far as is reasonably practicable? If not treated during design, a recommended action for others should be included here | Why is it not practicable to use a treatment control that is higher in the control hierarchy? | Who is responsible for putting the control action into place? | What is the consequence severity rating following implementation of the control action? | What is the likelihood rating following implementation of the control action? | What is the residual risk level following implementation of the control action?
2020-02-25 | Open | EXAMPLES | Design | Live Services | DBYD plans show burried HV electrical cable & HP gas within close proximity to the proposed pipe route, and geotechnical investigations require destructive excavation techniques to recover soil samples. | Service strike during excavation may result in serious injury or death. | Major | Possible | leave blank | High | Engineering | Prior to geotechncial excavations, GPR & Electromagnetic service location shall be performed on site to ensure the excavation area is clear of services. | Western Power and ATCO gas have been contacted and would not allow isolation of the live services. The geotechncial advisor indicated borehole testing should not be substituted (based on risk), however advised that the location of the boreholes could be adjusted based on the location of underground services. | Designer | Major | Rare | Moderate | leave blank | OpenHigh | OpenModerate
2020-02-25 | Open |  | Construction & Commissioning | Live Services | Installation of the DN700 pipe requires excavation under a live DN300 rubber ring jointed reinforced concrete pressure main at approx chaninage 350m. | If the concrete presure main is not isolated and sufficiently supported during excavation for the DN700, the pipe may fail at the joints, resulting in engufment in the trench and possible death due to drowning. | Major | Possible | leave blank | High | Isolation | Prior to excavating under the DN300, the John St Waste Water Pump Station is to be isolated following Water Corporaitons LOTO procedure. CTW3 is to be approved by PRA prior to any excavation around the DN300. The DN300 is to be adequately supported (may include reducing the width of the trench by using shoring and/or slinging the pipe from a beam above the trench). The trench shall have a suitable means of egress. | The alternative pipe route would have avoided clashing with the DN300, however would have added 800m to the pipeline length, so was not recommended. Due to minimum pipe cover restrictions, it was not possible to run the new DN700 above the existing DN300. | Contractor | Major | Rare | Moderate | leave blank | OpenHigh | OpenModerate
2020-02-25 | Open |  | Operations & Maintenance | Falls: Working at Heights, Falling Objects | The proposed solar panels are located on a 4m high pole and will require maintenance | Fall from heights or dropped object resulting in a Lost Time Injury | Moderate | Possible |  | High | Engineering | The design has incorporated a pole with a lowering device (tilting hinge pole) to engineer out the need to work at heights | To meet security requirements, the solar panels needed to be located at a minimum height of 4m, so could not eliminate the 4m pole. Options analysis indicated that a western power connection was not feasible, so it was not practical to substitute the solar pannel. If the O&M staff are not aware of how to operate the tilting pole, there is a chance of working at heights, however the likelyhood of this is considered rare. | Designer, Contractor, Maintenance Staff | Moderate | Rare | Low |  | OpenHigh | OpenLow
2020-02-25 | Open |  | Decommissioning | Asbestos | The existing switchboard within the pump station building contains asbestos components | Asbestos fibre inhalation during decommissioning of the switchboard may result in diseases causing premature death | Major | Possible | leave blank | High | Administrative | Section 8.1 of the PSP states that the contractor is to complete an Asbestos Management Plan prior to the possession of site. As a minimum, the contractor shall have the relevant training and wear appropriate PPE for the removal of the switchboard. | Elimination and substitution not possible as the asbestos containing switchboard needs to be removed as part of the pump station decommissioning. No engineering controls have been identified. Providing the contractor follows a suitable methodology and uses appropriate PPE, the level of risk will be reduced to a moderate level. | Contractor | Major | Rare | Moderate | leave blank | OpenHigh | OpenModerate
|  | 1 |  | Access covers |  |  |  |  | leave blank
|  | 2 |  | Access/egress, access ways, entrances/gates
|  | 3 |  | Adjacent structures | [13 empty] | leave blank
|  | 4 |  | Amenities and Facilities | [13 empty] | leave blank
|  | 5 |  | Biological | [13 empty] | leave blank
|  | 6 |  | Brownfield Sites | [13 empty] | leave blank
|  | 7 |  | Carcinogens | [13 empty] | leave blank
|  | 8 |  | Commissioning | [13 empty] | leave blank
|  | 9 |  | Communications, e.g., normal, emergency | [13 empty] | leave blank
|  | 10 |  | Community/public interaction/access | [13 empty] | leave blank
|  | 11 |  | Confined space | [13 empty] | leave blank
|  | 12 |  | Construction interfaces | [13 empty] | leave blank
|  | 13 |  | Construction method | [13 empty] | leave blank
|  | 14 |  | Contamination | [13 empty] | leave blank
|  | 15 |  | Corrosion | [13 empty] | leave blank
|  | 16 |  | Dust/fumes/vapours
|  | 17 |  | Electrical
|  | 18 |  | Electrical / Arc Flash
|  | 19 |  | Emergency Response
|  | 20 |  | Energy Release
|  | 21 |  | Ergonomics
|  | 22 |  | Erosion
|  | 23 |  | Excavation Collapse/Engulfment
|  | 24 |  | Explosives
|  | 25 |  | External / third party activities
|  | 26 |  | Extreme weather
|  | 27 |  | Falls: Working at Heights, Falling Objects
|  | 28 |  | Fatigue
|  | 29 |  | Fire
|  | 30 |  | Fixed plant and equipment
|  | 31 |  | Flow
|  | 32 |  | Formwork
|  | 33 |  | Ground conditions
|  | 34 |  | Groundwater
|  | 35 |  | Guarding/fencing/security
|  | 36 |  | Hazardous Materials: Asbestos
|  | 37 |  | Hazardous Materials: Chemicals / Dangerous Goods (including compressed air receivers and surge vessels)
|  | 38 |  | Hazardous Materials: Hazardous Areas (Flammable Atmospheres)
|  | 39 |  | Hazardous Materials: Other
|  | 40 |  | Hot works
|  | 41 |  | Inspections
|  | 42 |  | Instability
|  | 43 |  | Interference between trades
|  | 44 |  | Laydown areas
|  | 45 |  | Lifting Devices/ Davits
|  | 46 |  | Lifting operations/cranage
|  | 47 |  | Lighting
|  | 48 |  | Live services
|  | 49 |  | Location
|  | 50 |  | Maintainability
|  | 51 |  | Manual handling
|  | 52 |  | Materials of construction
|  | 53 |  | Materials/ Chemicals in Contact with Drinking Water
|  | 54 |  | Mobile Plant and Equipment
|  | 55 |  | Movement of machinery/contaminants
|  | 56 |  | Noise
|  | 57 |  | Operations, including work practices
|  | 58 |  | Operations/interactions
|  | 59 |  | Overhead/underground services
|  | 60 |  | Piling
|  | 61 |  | Pollution/contamination/ spills /releases/emissions
|  | 62 |  | Pressure (High/Low)
|  | 63 |  | Programmable Logic Controllers (PLC)
|  | 64 |  | Public interference
|  | 65 |  | Radiation
|  | 66 |  | Railways
|  | 67 |  | Restricted Areas
|  | 68 |  | Reuse of existing assets
|  | 69 |  | Safety factor
|  | 70 |  | Sanitation/hygiene/waste
|  | 71 |  | Services
|  | 72 |  | Slips/trips/falls
|  | 73 |  | Start-up/shutdown
|  | 74 |  | Storage
|  | 75 |  | Structures
|  | 76 |  | Temperature
|  | 77 |  | Temporary works
|  | 78 |  | Unexploded Ordinances
|  | 79 |  | Vehicles & trucks: Including Movement of People and Materials
|  | 80 |  | Vibration
|  | 81 |  | Visibility
|  | 82 |  | Waste
|  | 83 |  | Water
|  | 84 |  | Workplace conditions, extreme temperatures
| Rows can be added by dragging down from row97. | [17 empty] | Rows can be added by dragging down from row97. | Rows can be added by dragging down from row97.
| Rows and content can be deleted when not applicable to the Design | [17 empty] | Rows and content can be deleted when not applicable to the Design | Rows and content can be deleted when not applicable to the Design
EXAMPLES ONLY -
DELETE FROM FINAL SiD REPORT

## SiP RISK REGISTER
*Safety in Planning Risk Register to be deleted from Safety in Design Report prior to handover to Contractor
Safety in Planning - RISK REGISTER | [10 empty] | # not treated | 0 | # Substitution | 0
C00000 - Water Corporation SAP Project Number & title | [5 empty] | # of open risks | 0 |  |  |  | # PPE | 0 | # Isolation | 0
Date | [5 empty] | # of closed risks | 0 |  |  |  | # Administrative | 0 | # Elimination | 0
PREPARED BY: | [10 empty] | # Engineering | 0
APPROVED BY:
|  |  | 1. Hazard Identification |  |  | 2. Initial (Uncontrolled) Risk Assessment |  |  |  |  | 3. Risk Treatment |  |  |  | 4. Residual Risk Assessment
Date Entered/ Updated | Risk Status | Ref | Asset Life cycle Stage | Hazard Guideword | Hazard Description | Consequence Description | Consequence severity rating | Likelihood rating | Retained Risk | Risk level | Treatment Control Type | Action Description | Why Higher Treatment Control not Adopted? | Action Assignee | Consequence severity rating | Likelihood rating | Risk level
The latest revision date should be included here | Closed Risk Status applies to hazards that have no residual risk (i.e. the hazard has been eliminated for the relevant lifecycle stage), or the lifecycle is complete so the risk is no longer relevant (i.e. design is complete so risks in the Design Life Cycle Stage are now Closed) | # | When will the hazard be encountered? (not necessarily when the hazard will be treated) | Guidewords are used to help identify hazards. Refer to 'Water Corporation Guidewords' tab | What is the potential source of harm? | What could happen and who could be affected? | Refer to Consequence rating table under 'Risk Assessment Criteria' tab | Refer to Likelihood rating table under 'Risk Assessment Criteria' tab |  | Refer to Risk Matrix under 'Risk Assessment Criteria' tab | Using the control hierarchy, the highest practical control should be implemented, or listed as a recommendation for others | What has been done to reduce the risk so far as is reasonably practicable? | Why is it not practicable to use a treatment control that is higher in the control hierarchy? | Who is responsible for putting the control action into place? | What is the consequence severity rating following implementation of the control action? | What is the likelihood rating following implementation of the control action? | What is the residual risk level following implementation of the control action?
|  | EXAMPLES | [6 empty] | leave blank | #N/A | [6 empty] | #N/A | leave blank | #N/A | #N/A
[9 empty] | leave blank | #N/A | [6 empty] | #N/A | leave blank | #N/A | #N/A
[10 empty] | #N/A | [6 empty] | #N/A |  | #N/A | #N/A
[9 empty] | leave blank | #N/A | [6 empty] | #N/A | leave blank | #N/A | #N/A
|  | 1 |  | Access covers |  |  |  |  | leave blank
|  | 2 |  | Access/egress, access ways, entrances/gates
|  | 3 |  | Adjacent structures | [13 empty] | leave blank
|  | 4 |  | Amenities and Facilities | [13 empty] | leave blank
|  | 5 |  | Biological | [13 empty] | leave blank
|  | 6 |  | Brownfield Sites | [13 empty] | leave blank
|  | 7 |  | Carcinogens | [13 empty] | leave blank
|  | 8 |  | Commissioning | [13 empty] | leave blank
|  | 9 |  | Communications, e.g., normal, emergency | [13 empty] | leave blank
|  | 10 |  | Community/public interaction/access | [13 empty] | leave blank
|  | 11 |  | Confined space | [13 empty] | leave blank
|  | 12 |  | Construction interfaces | [13 empty] | leave blank
|  | 13 |  | Construction method | [13 empty] | leave blank
|  | 14 |  | Contamination | [13 empty] | leave blank
|  | 15 |  | Corrosion | [13 empty] | leave blank
|  | 16 |  | Dust/fumes/vapours
|  | 17 |  | Electrical
|  | 18 |  | Electrical / Arc Flash
|  | 19 |  | Emergency Response
|  | 20 |  | Energy Release
|  | 21 |  | Ergonomics
|  | 22 |  | Erosion
|  | 23 |  | Excavation Collapse/Engulfment
|  | 24 |  | Explosives
|  | 25 |  | External / third party activities
|  | 26 |  | Extreme weather
|  | 27 |  | Falls: Working at Heights, Falling Objects
|  | 28 |  | Fatigue
|  | 29 |  | Fire
|  | 30 |  | Fixed plant and equipment
|  | 31 |  | Flow
|  | 32 |  | Formwork
|  | 33 |  | Ground conditions
|  | 34 |  | Groundwater
|  | 35 |  | Guarding/fencing/security
|  | 36 |  | Hazardous Materials: Asbestos
|  | 37 |  | Hazardous Materials: Chemicals / Dangerous Goods (including compressed air receivers and surge vessels)
|  | 38 |  | Hazardous Materials: Hazardous Areas (Flammable Atmospheres)
|  | 39 |  | Hazardous Materials: Other
|  | 40 |  | Hot works
|  | 41 |  | Inspections
|  | 42 |  | Instability
|  | 43 |  | Interference between trades
|  | 44 |  | Laydown areas
|  | 45 |  | Lifting Devices/ Davits
|  | 46 |  | Lifting operations/cranage
|  | 47 |  | Lighting
|  | 48 |  | Live services
|  | 49 |  | Location
|  | 50 |  | Maintainability
|  | 51 |  | Manual handling
|  | 52 |  | Materials of construction
|  | 53 |  | Materials/ Chemicals in Contact with Drinking Water
|  | 54 |  | Mobile Plant and Equipment
|  | 55 |  | Movement of machinery/contaminants
|  | 56 |  | Noise
|  | 57 |  | Operations, including work practices
|  | 58 |  | Operations/interactions
|  | 59 |  | Overhead/underground services
|  | 60 |  | Piling
|  | 61 |  | Pollution/contamination/ spills /releases/emissions
|  | 62 |  | Pressure (High/Low)
|  | 63 |  | Programmable Logic Controllers (PLC)
|  | 64 |  | Public interference
|  | 65 |  | Radiation
|  | 66 |  | Railways
|  | 67 |  | Restricted Areas
|  | 68 |  | Reuse of existing assets
|  | 69 |  | Safety factor
|  | 70 |  | Sanitation/hygiene/waste
|  | 71 |  | Services
|  | 72 |  | Slips/trips/falls
|  | 73 |  | Start-up/shutdown
|  | 74 |  | Storage
|  | 75 |  | Structures
|  | 76 |  | Temperature
|  | 77 |  | Temporary works
|  | 78 |  | Unexploded Ordinances
|  | 79 |  | Vehicles & trucks: Including Movement of People and Materials
|  | 80 |  | Vibration
|  | 81 |  | Visibility
|  | 82 |  | Waste
|  | 83 |  | Water
|  | 84 |  | Workplace conditions, extreme temperatures
| Rows can be added by dragging down from row97. | [17 empty] | Rows can be added by dragging down from row97. | Rows can be added by dragging down from row97.
| Rows and content can be deleted when not applicable to the Design | [17 empty] | Rows and content can be deleted when not applicable to the Design | Rows and content can be deleted when not applicable to the Design
EXAMPLES ONLY -
DELETE FROM FINAL SiP RISK Register

## Risk Assessment Criteria
Risk Assessment Criteria
Likelihood rating table
| Descriptor | Description | Frequency
| Almost Certain | The event is expected or known to occur more than once per year | Will occur more than once a year
| Likely | Known to re-occur approximately annually. Known to occur across like industries or within corporation. | Will occur once per year
| Possible | The event should occur at some time. Has occurred several times across like industries. | Will occur once every 5 years
| Unlikely | The event could occur at some time. Known to have occurred once or twice within industry. | Will occur once in 10 years
| Rare | The event may occur in exceptional circumstances. An example of this has occurred historically, but is not anticipated. | Will occur once in 30 years or less
Risk Matrix
Likelihood
| Consequence rating table |  |  |  |  | Rare | Unlikely | Possible | Likely | Almost Certain | N/A - Hazard Eliminated | Risk level
| Catastrophic | Multiple fatalities, and/or Onset of lift shortening illness for multiple persons |  | Consequence | Catastrophic | High | High | Extreme | Extreme | Extreme | Risk Closed | E Extreme | 5 Catastrophic | E Rare | 5 CatastrophicE Rare | High
| Major | Single Fatality, and/or Injury/illness resulting in significant permanent disabillity or life shortening illness |  |  | Major | Moderate | High | High | Extreme | Extreme |  | H High | 5 Catastrophic | D Unlikely | 5 CatastrophicD Unlikely | High
| Moderate | Injury, illness, requiring speciallist medical treatment, or Hospitalisation, resulting in loss of functional ability (Restricted Work Injury- RWI), or Time off work (Lost Time Injury- LTI) |  |  | Moderate | Low | Moderate | High | High | High |  | M Moderate | 5 Catastrophic | C Possible | 5 CatastrophicC Possible | Extreme
| Minor | Injury/illness requireing medical treatment, nil loss of functional ability (Medical Treatment Injury- MTI) |  |  | Minor | Low | Low | Moderate | High | High |  | L Low | 5 Catastrophic | B Likely | 5 CatastrophicB Likely | Extreme
| Insigificant | Injury/illness requiring no treatment or first aid treatment only (Minor Injury- MI) |  |  | Insignificant | Low | Low | Low | Moderate | Moderate |  | N/A | 5 Catastrophic | A Almost Certain | 5 CatastrophicA Almost Certain | Extreme
[5 empty] | N/A - Hazard eliminated | Risk Closed | [5 empty] | ?? | 4 Major | E Rare | 4 MajorE Rare | Moderate
[12 empty] | Risk status | 4 Major | D Unlikely | 4 MajorD Unlikely | High
[12 empty] | Open | 4 Major | C Possible | 4 MajorC Possible | High
[12 empty] | Closed | 4 Major | B Likely | 4 MajorB Likely | Extreme
[13 empty] | 4 Major | A Almost Certain | 4 MajorA Almost Certain | Extreme
[12 empty] | Control Hierarchy | 3 Moderate | E Rare | 3 Moderate E Rare | Low
[12 empty] | Elimination | 3 Moderate | D Unlikely | 3 Moderate D Unlikely | Moderate
Substitution
[12 empty] | Isolation | 3 Moderate | C Possible | 3 Moderate C Possible | High
[12 empty] | Engineering | 3 Moderate | A Almost Certain | 3 Moderate A Almost Certain | High
[12 empty] | Administrative | 2 Minor | E Rare | 2 MinorE Rare | Low
[12 empty] | PPE | 2 Minor | D Unlikely | 2 MinorD Unlikely | Low
[13 empty] | 2 Minor | C Possible | 2 MinorC Possible | Moderate
[12 empty] | Life cycle phase | 2 Minor | B Likely | 2 MinorB Likely | High
[12 empty] | Planning | 2 Minor | A Almost Certain | 2 MinorA Almost Certain | High
[12 empty] | Design | 1 Insignificant | E Rare | 1 InsignificantE Rare | Low
[12 empty] | Construction & Commissioning | 1 Insignificant | D Unlikely | 1 InsignificantD Unlikely | Low
[12 empty] | Operations & Maintenance | 1 Insignificant | C Possible | 1 InsignificantC Possible | Low
[12 empty] | Decommissioning | 1 Insignificant | B Likely | 1 InsignificantB Likely | Moderate
[12 empty] | Control effectiveness | 1 Insignificant | A Almost Certain | 1 InsignificantA Almost Certain | Moderate
O
go to top | [11 empty] | A
I

## Water Corporation Guidewords
Water Corporation Engineering Business Unit - Risk Guidewords
GUIDEWORDS
Describes general area of the hazard | Considerations | WC Risk Ref #
Access covers | Are lid covers appropriate? (“Gatic” covers used only in traffic areas otherwise lightweight material to reduce manual handling issues) Are there hardstand around “Gatic” lids to allow use of lifters and space to place lid? Is ground level/no slopes? Is there a locking facility on lightweight lids? Is there internal grate facility to prevent falls? | 1
Access/egress, access ways, entrances/gates | How should people enter or exit the site or gain access to individual asset/item? Does Vehicle access to the site allow adequate clearances for the types of vehicles expected to service the facility? Are there adequate parking facilities? Are the surfaces adequate for all weather access? Are hazardous areas restricted from vehicles? ie drains, valve pits, operator work areas. Are bollards or other requirements used to restrict as appropriate? Is vehicle access within buildings designed well? ie clearances, protection of operators at doorways, parking restrictions. Has size of doors and gates been considered with respect to ease of operation in strong wind? Is the size and placement of doors and gates appropriate for removal of equipment? Are there fastening points to hold doors and gates in open position? Are handles appropriate so restraint can be applied without hand pinch injuries? | 2
Adjacent structures | How do structures adjacent to the design affect the design and/or how will the design affect things that surround it? e.g. heat, light, shadow, geotech stability, fire, access. | 3
Amenities and Facilities | Will amenities and facilities be required? e.g. Is access to various amenities and facilities such as storage, first aid rooms/sick rooms, rest rooms, meal and accommodation areas and drinking water necessary and been provided? | 3
Biological | Does the design use, produce or dispose of substances known to be biological hazards? Does the construction site potentially include biologically hazardous material? e.g. wastewater treatment solids. | 4
Brownfield Sites | Has the design considered how the existing conditions of the site and how the existing assets would affect the safety of personnel and the new assets that are to be constructed or installed? Consider whether all the existing utilities assets been identified and located and whether they are they fit for purpose to support the new assets? Are demolition or decommissioning activities required? Are personnel adequately separated and protected from existing chemicals? Is emergency response planning affected by construction activities? Would the existing chemicals affect the segregation and storage of the new chemicals? Would they affect the Dangerous Goods (DG) licencing and other regulatory requirements? | 5
Carcinogens | Does the design use, produce or dispose of substances known to cause cancer? | 6
Commissioning | How can the act of commissioning generate hazards? | 6
Communications, e.g., normal, emergency | Is communication at the site a safety issue? Does the design consider critical communication events such as emergencies (response time) and is there mobile phone coverage? | 14
Community/public interaction/access | Is there public access to the site or is there potential community interaction? Does the design provide sufficient controls to prevent harm to the public? Does construction vehicle movement pose a risk? | 14
Confined space | Are there confined spaces created by the design? Has the design minimised the need for confined space entry, looking for alternate methods of accessing and operating equipment? Have they been indicated on the drawings and are there alternative methods that can be developed/used to eliminate and/or reduce the impacts of confined spaces? Are the sizes of pits adequate for safe entry? Are work areas and clearances adequate in base of pits to perform maintenance and repair/install equipment? Are davit points included where needed? Are there adequate hardstand areas around lids to ensure safe opening and operation of any equipment? Is there sufficient drainage away from lids and pit walls? Can equipment be operated without entering confined areas? (ie extended valve spindles) | 17
Construction interfaces | Does the proposed construction interface with other operating works? Consider all interfaces that will require a Clearance to Work (CTW) permit. Have these been indicated on the drawings and has the use of a CTW been noted as a mitigation in the Safety in Design Risk Register? Consider: • Where coring through existing concrete slab or excavating and there may be concealed services • Pipe cut-ins to existing services • Overhead power lines • Anything else where the operational contact deems it appropriate The location of all such points on the site should be clearly shown on location plan drawings (refer to HK42-3-2 as an example for CTW for cut-ins.) For CTW near concealed services the designer shall review relevant services drawings while selecting interface locations to avoid possible clashes with the excavating, coring or drilling and services. Details of CTW points on drawings should specify: • that the contractor shall check the as-con drawing for all existing services including concealed services; • that the contractor shall detect existing services on site prior to excavating, coring or drilling and mark them on site. | 17
Construction method | Does the method of construction introduce hazards? e.g. tilt-up or precast concrete work, post tension concrete work, tunnelling, demolition, etc What construction options are available? | 17
Contamination | Does existing contamination or that introduced by the design or construction pose a risk? Consider whether contamination from construction, the process or waste streams could be reduced or eliminated Design Managers should consult Spatial Information Management for existing known locations of contaminated sites. | 19
Corrosion | Is there a corrosion risk due to either the environment or process? The design should consider materials selection to reduce the risk. | 19
Dust/fumes/vapours | Could dust, fumes and/or vapours be produced during construction, commissioning or operations? Is exposure to volatile organic compounds and off-gassing through the use of composite wood products or paints a risk? How does the design minimise their possibility and consequence? | 19
Electrical | Does the design introduce the risk of electric shock? • Underground power cables • Proximity to exposed cables • Work near overhead power lines Consider risks introduced by electrical services (i.e. contact with power lines or voltage induction by steel pipelines running parallel to overhead services). Consider earthing requirements (including fencing and gates) Consider number and location of power points. | 19
Electrical / Arc Flash | Will the design alter the following: · Maximum demand of the site? · Protection settings of the primary incomer? · Protection types? · Primary and secondary switching devices? · Power transformer ratings? · Cables or Busbar sizes? · Types of loads added to the site, inductive or capacitive If any of the above aspects have been altered as a result of the new design then the switchboard will require a new arc flash model completed in accordance with DS29 to determine the new arc flash risk rating. | 27 | New item on 18/7/2019
Emergency Response | Is emergency response a special risk for this project? How does the design consider how to provide emergency response? Aspects to consider include provision of first aid, communication, access for emergency services and evacuation. | 30
Energy Release | Does the design include the potential for stored energy? Does the design address stored energy impacts and provide adequate and appropriate methods to eliminate or reduce those impacts? Has the design identified all the energy sources requiring isolation and does the design consider the location and number of isolation points? (especially an issue for brownfield sites where As Constructed information on pipework may not be accurate). Are emergency isolation switches in easily accessible locations? (e.g. For electrical isolation of pumps, cranes or isolation points of chemical doing lines) Is there mechanical/physical isolation to protect against exposure to high pressure? Is lock out capability available at all isolation points? Does the design require isolation of existing assets during construction and is that isolation possible? Does the integrity of that isolation need to be checked? | 30
Ergonomics | Are there likely ergonomic risks with the design? How do humans interact with the design? Are workstations or operator controls designed to allow ease of use for the human body? Is there adequate clearance around equipment including electrical cabinets to allow maintenance and operation? Is there clearance to remove/install equipment without restricting access? Is there access to any crane/lifting equipment and their controls? Can all equipment be operated safely and at the correct height? | 35
Erosion | Is there a risk of ground erosion or erosion of piping and plant due to industrial process? Consider erosion due to stormwater run-off concentration of flow or wind and process discharge points | 35
Excavation Collapse/Engulfment | Is there a possibility that risks such as excavation collapse or flooding will be introduced? Is the working corridor for the excavation sufficient? Is it been impacted by any external approval constraints? Does the design require deep excavations to pipes for maintenance that may result in an unsafe work environment or that may impact adjacent assets? Can this be avoided? | 36
Explosives | Does the design include any substances that could lead to explosion, including gases, liquids or dust? Will explosives be used during construction? Will work be occurring in or adjacent to areas classified as Hazardous (flammable) Areas? Have sources of ignition been eliminated and monitoring systems been included? | 37
External / third party activities | Are there any external/third parties issues, including the need for access by local council, service providers or other agencies? | 38
Extreme weather | Is extreme weather a possible factor for the design or construction? Has the design included the provision of shelter or reduction of the effect of extreme weather on people? Has the design considered loads capable of withstanding the effects of weather, such as high winds, rain, heat and cold? Consider impact on plant and equipment (i.e high temperature impacting on electrical equipment) | 38
Falls: Working at Heights, Falling Objects | Is working at heights an issue for construction or operations/maintenance? Is there a possibility of objects being dropped from heights or into pits where people may be working? Has the design considered height related impacts and provided adequate and appropriate methods to eliminate and/or reduce those impacts based on the Corporate Standard? Have adequate fall prevention controls been provided? e.g. guard rails, kick plates, anchorage points for fall prevention systems, allowance for Kennedy Barriers, scaffolding, temporary work platforms, appropriate roof materials and surface characteristics (such as fragility, slip resistance and pitch). Has protection been included, including barriers to stop objects from falling and covers to protect from objects that have fallen? Are fall protection grates required in openings to pits? | 39
Fatigue | Does the design introduce potential human fatigue issues? | 44
Fire | Does the design include flammable or combustible materials? Is there an offsite fire risk? (e.g. neighbouring bush) Are fire detection systems and fire-fighting systems necessary? Have emergency routes and egress been identified? Are any other emergency facilities required? Is there access for fire tenders? Is the new asset in an area which may be subject to a bushfire risk? If so: - Is there a cleared 20 meter asset protection zone (non-flammable) between any critical operational structural elements and the standing fuel load; - If unable to achieve a minimum 20m asset protection zone, has the structural fabrication of the asset been assessed for suitability? Are there ember screens; no gutters or downpipes; a skillion, gabled or similar angled roof; all gaps between roller doors and other fenestrations upon the asset are covered. | 45
Fixed plant and equipment | Are there any risks introduced associated with the location of fixed plant and equipment? | 49
Flow | Are there any risks introduced associated with flow? Have hazards associated with too much flow, not enough flow or blockages been considered? | 49
Formwork | Does the design include formwork during construction? Have hazards such as heights, slips and trips, engulfment and confined spaces been considered? Has the potential for form collapse during concrete pours been managed? | 56
Ground conditions | Are ground conditions a risk factor? Does the design take into account the general terrain and type of ground? How the asset should alter the ground conditions, are there any introduced risks? | 57
Groundwater | Does groundwater produce the possibility of unstable ground, corrosion of underground assets or structural instability? | 58
Guarding/fencing/security | Are there risks introduced relating to guarding / fencing / barriers and/or security? Is plant and equipment guarded appropriately? E.g. preventing contact with energies, interlock, tamper proof, fails to safe etc. Does the design provide sufficient security measures to protect the asset? Has the asset been subject to vandalism or break-in in the past? Has appropriate security signage been identified and specified? e.g. fencing, alarms, electronic surveillance, etc. | 62
Hazardous Materials: Asbestos | Could asbestos be present, including as material in existing buildings or piping on or adjacent to the site? Is asbestos contained or exposed with the possibility of dust formation? Is asbestos contained or exposed with the possibility of dust formation? Will there be Coal Tar or Bituminous Coated Pipes and can the design be adjusted to avoid working on or around this material? Refer to the guideline “Working on Asbestos Coated Pipes” (AquaDOC # 14765700) for more information. If work on the pipeline cannot be avoided ensure the hazard is identified and communicated to the construction contractor. Consider that even when a site has been assessed or inspected by a competent person and no ACM has been identified, further site work may uncover potential ACM in inaccessible areas not previously inspected. For example by excavation, by Have the steps taken to identify and locate asbestos containing material been documented? Has the extent and location of asbestos containing material (ACM) on site been established? (through consultation of the asbestos register and desktop analysis of any as constructed drawings) Note, the Asbestos Register details the location of previously identified ACM, it should not be relied upon to confirm no ACM is present? Consider the need for an inspection by competent person to be undertaken, if determined necessary. Refer to the following guideline (AquaDOC #14091571) for more information on the type of inspection that may be required. Has the management of identified ACM been addressed? Has the management of previously unidentified ACM that may be uncovered during construction been addressed? | 63
Hazardous Materials: Chemicals / Dangerous Goods (including compressed air receivers and surge vessels) | Does the design use, produce or dispose of chemicals? Does the project involve works in close proximity to existing chemicals? Refer: List of Chemicals Are dangerous goods or hazardous chemicals required? Are there alternatives available that may be less harmful to both people and the environment? Has the design adequately considered separation of chemicals and pipework, from personnel and segregation from other chemicals? Has the design incorporated chemical barrier protection, storage segregation, separation and bunding? Has the design addressed protection of chemicals from impact, fire and ignition sources? Has spill containment been addressed? Has safety shower access been adequately provided? Location and access to showers, are guard rails required to access showers? Is there adequate delivery facilities and truck turning circles? Adequate facilities to transfer chemicals? Is there PPE storage and SCBA location if required? (Accessible cabinets and good storage location on site) Is there adequate signage in the design? Is there a disposal facility? Is there measurement/monitoring facility? Are licensing and ERP requirements covered? Is there ventilation? Is a wind sock required? Has DS79 been complied with? (including Appendix 1 - DG requirements, Hazardous Area Classification and Pressure Vessel registration) | 65
Hazardous Materials: Hazardous Areas (Flammable Atmospheres) | Does the design include (or potentially include) the creation hazardous areas (flammable atmospheres)? Is there the potential for explosion due to the presence of dust or explosive gases (e.g. methane, hydrogen, ammonia, methanol etc.) either under normal operation or during a fault condition? Consider relevance in particular on Wastewater and Electrochlorination projects
Hazardous Materials: Other | Does the project involve exposure to hazardous substances (e.g. bio-waste) and materials, including insulation and decorative materials? Has such exposure been eliminated or mitigated? | 65
Hot works | Are hot works during construction and operations a potential source of risk? Have they been taken into account in the design? | 007, 019
Inspections | Does the design consider the necessity of inspections and allow for access, lighting, guarding, etc? | 007, 064
Instability | Is instability due to structures or geotechnical conditions a risk? Is the new process (e.g. treatment) introducing an instability risk? Have fail-safe measures been addressed? | 011, 012, 014, 015
Interference between trades | Is the interaction between the different trades during construction and operation a risk? Has it been considered in the design? | 014, 015, 022
Laydown areas | Are laydown areas a source of risk? Does the laydown area provide sufficient space to allow safe access to equipment and are laydown areas located in positions that provide short and unobstructed travel paths? | 044, 060
Lifting Devices/ Davits | Are they required? Are they located correctly? Can they function without fowling on other equipment or structure? Are they rated correctly for the purpose? If used for equipment or personnel, are access points correct? Is a hardstand area required as a receival point for loading/unloading? Is the cabling and controls protected from the elements? | 046, 039
Lifting operations/cranage | Are heavy lifts/cranage involved? Has the design required delivery of unusually large, awkward or heavy items of equipment (including unusually long pipelines lengths, switchgear, prebuilt machinery or package plants, etc) Can heavy lifts be removed or minimised? Is there sufficient room to allow access for cranes and for the cranes to operate? | 050, 067
Lighting | Is lighting a source of risk? Has sufficient lighting been provided to allow the design to perform as required and to allow personnel to operate the design as required? Has easy maintenance access to lighting been addressed? Adequate internal and external lighting? Has control of lighting been considered (manual or auto) Has emergency lighting requirements on UPS been included? Is there appropriate access to lighting for maintenance? | 061, 066
Live services | Are live services a source of risk? Have services such as electricity, gas, compressed air, fuel, water, sewer and telecommunications been identified and isolation or relocation of these services been included in the design? Are they operable/fit for purpose?
Location | Is the location of the site itself in relation to the environment and other assets surrounding it a risk? Have the locations of the assets within the design been considered with respect to each other and any existing assets already in place? Are different sections of a design compatible to be located beside one another?
Maintainability | Is maintainability a risk in this case? Has the design provided for maintenance of the asset with clear working space provided, lifting device/points provided, prevention of falls features and the risk hazard such as electricity, heat, pressure and vibration eliminated or reduced as far as is practicable and that appropriate signage (warning, caution, danger) have been specified in the design? Are there adequate scouring points for disposal of water during maintenance? Doe the pipework configuration allow for easy removal of valves? Are all underground assets identified so they can be recorded in MyWorld?
Manual handling | Is manual handling required by the design? Has the design considered mechanical devices for lowering and lifting equipment and is the equipment positioned so it can be retrieved/replaced using mechanical devices and does the equipment have designated designed lifting points? Has accessibility for manual handling been adequately addressed? e.g. Access and egress paths and doorways to facilitate movement or other mechanical aids. Have all manual bulk handling tasks been considered for mechanisation? (e.g. Hopper or vacuum fed dosing systems) Are there any heavy UPS batteries in or outside of cabinets? Is there sufficient open space to allow lifting aids and trolleys to access the batteries so they can be easily removed and installed by maintenance staff?
Materials of construction | Are there any special materials of construction issues? Does the design consider the selection of materials relative to the location of the asset (e.g. can it handle bushfires) construction technique required, maintenance requirements (uniformity vs mixing) etc? Does the design consider opportunities to source material through reuse or recycled options?
Materials/ Chemicals in Contact with Drinking Water | Are there any new materials or chemicals being used? Chemicals added to drinking water or materials in contact with drinking water must be approved by Department of Health. Obtain advice from IDB Water Treatment Principal Engineer.
Mobile Plant and Equipment | Is the movement of mobile plant (includes vehicles) required and therefore a source of risk? Has it been addressed in the design?
Movement of machinery/contaminants | Is the need to have clear paths for machinery (e.g. elevated work platforms, forklifts, etc) movement a source of risk? Has the design eliminate impacts where possible, or mitigated them where not? This includes impacts with humans, machinery, structures or vehicles. Are floor slabs designed to take crane loads?
Noise | Does the design require noisy processes to be used during construction that may affect personnel or neighbours? Are there ways to eliminate and/or reduce impacts through alternative design measures or by using construction methodologies? Have plant and equipment that create noise been appropriately designed to reduce noise? e.g. ceramic bearings, dampers, isolated, insulated, balanced to reduce vibration, located in rooms with noise attenuation etc.
Operations, including work practices | Does the design introduce new working procedures or practices? Is space required for operations related equipment and furniture? (e.g. PPE cabinets, computer desks, refrigerators, chairs and tables, cupboards, etc)
Operations/interactions | Is there a risk with how the new project interfaces with existing assets?
Overhead/underground services | Does the design potentially interact with existing services? e.g. striking underground and overhead services (including electricity, gas, communications, water, wastewater etc), access for construction, maintenance and operational vehicles and plant and excavation and can the design be modified to eliminate and/or reduce the impact associated with the existing services?
Piling | Is piling a likely requirement for construction? Have the hazards associated with piling been considered for the piling operation and on the surroundings? Hazards include the stability of piling rig including geotech investigation, dropped weights, heights, excavations, noise and vibration.
Pollution/contamination/ spills /releases/emissions | Is: pollution, contamination, spills, releases, emissions a risk? Does the design consider these issues to reduce or eliminate the impacts?
Pressure (High/Low) | Has the design identified processes or the use of plant and/or equipment that have the potential for high or low/negative pressure? Has the impact of those pressures during construction, maintenance and operation of the asset and the controls to prevent uncontrolled release of those pressures whilst carrying out maintenance and/or emergency operations been addressed? Does the design include the use of pressure? Have sufficient confinement, materials of construction, testing, pressure relief systems and isolation been considered in the design? Are they operable/fit for purpose?
Programmable Logic Controllers (PLC) | Does the design include a PLC? Does the design include measures to ensure safe functioning of the asset in the case of PLC failure? Have all failsafe conditions been identified and managed?
Public interference | Is public interference a significant risk? Has security of the assets included in the design been incorporated? Has the level of security required based on public perception been considered? Do all open pipes (drains, scours and overflows) have mesh security covers? Are all pits covered or railed? Appropriate locked facilities and entry points within the facility eg ladder and stairway security? Appropriate warning Signage?
Radiation | Does the design or construction include radioactive material or the generation of x-rays? Does any work occur in proximity to radio or mobile towers, or other sources of non-ionising radiation? Has the design considered containment, screening/shielding, elimination of the requirement, signage, sufficient space requirements around the radiation source and emergency procedures?
Railways | Will construction work occur in close proximity to railways?
Restricted Areas | Are restricted areas identified marked and protected? • signage, • handrails, • bollards, • floor markings, • appropriate locks (especially electrical cabinets), • Arc Flash boundaries
Reuse of existing assets | Is the existing asset capable of performing the required function adequately? Consideration should be given to testing the condition of the asset early in the project to avoid redesign and budget blowout if asset is found to be unsuitable much later in the project.
Safety factor | Is having a sufficient engineering over design factor a requirement in order to manage risk?
Sanitation/hygiene/waste | Is sanitation/hygiene/waste a risk for the project? What types of waste should be produced? How should it be collected and disposed of? How can the impacts be reduced?
Services | Are there services (other than “live services” or overhead/underground – e.g. unused or un-energised) that pose a risk? Does the design consider the impacts on existing services?
Slips/trips/falls | Check that all requirements have been identified ie elevation changes around buildings, cabinets, valves, equipment modules. Anything greater than 300mm may require a working platform and/or steps for safe access. Has possible paths of movement on the site been considered to determine needs? Is there suitable protection around cable and pipe locations where access over/under them is required? Are all ladders, walkways and platforms are located in the appropriate location and configuration is correct? Do ladder stiles extend past openings? Are top rungs level with platforms? Are ladder slopes, landings and cages appropriate? Are toe boards installed? Is clearance adequate? ie entry, exit and from any other structure or equipment Are handrails and openings correct, including protection of openings with chains or self-closing gates? Does the design include changes of grade or potential wet areas? Does the design provide for surfaces that are even and non-slip where necessary and clear walkways? • Avoid elevation changes on site including edges of concrete pads • No sloping surfaces in maintenance and access areas
Start-up/shutdown | Does the method of start-up or shutdown of a process introduce any hazards? Hazards may include isolations, ignition sources, pressure, gravity, speed and temperature.
Storage | Is there a need for storage? How are storage areas incorporated into the design?
Structures | Does the design incorporate ease of construction and access during operations and maintenance? Does the design incorporate the erection of steelwork or concrete frameworks during construction? Does the design incorporate the erection of temporary structures? Have load bearing requirements and stability/integrity of structures been adequately considered?
Temperature | Is temperature an issue for the design or construction activities? Does the design include protection from high and low temperatures, including protection for people and the equipment? Is the temperature necessary in the design? Does ventilation need to be considered? Is the amount of ventilation is adequate for temperature control? Do ventilation hatches on roofs have internal mesh to eliminate falling hazard? Does any mechanical ventilation meets requirements and includes signage?
Temporary works | Does the design/specification detail temporary works requirements e.g. weights of component, temporary lifting points, permanent formwork vs conventional formwork etc.
Unexploded Ordinances | Is UXO a risk? Has UXO risk been checked? The Department of Fire and Emergency services, and /or the Corporations Spatial information system should be checked for existing known locations of potential unexploded ordinances.
Vehicles & trucks: Including Movement of People and Materials | Is movement of people and vehicles (including those moving materials) a significant source of risk? Will the project impact on existing roads and/or traffic? Can impacts be eliminated and/or reduced? e.g., service point in road, access of roads, and access for construction, maintenance and operational vehicles, safe entry and exit from site Is there safe access and egress provided for people and vehicles? (including separation if necessary) Have traffic routes and control measures been identified if necessary? Have appropriately sized unloading bays and ramps been provided if necessary?
Vibration | Does the design include significant levels of vibration? Have the effects of vibration on the human body and the surrounding assets been considered in the design?
Visibility | Is lack of visibility an issue for the design?
Waste | Does the design include the potential to generate significant levels of waste? Has the design considered the reuse of materials and the potential disposal issues of existing material? Have opportunities to reduce waste been incorporated into the design?
Water | Does the design consider working in or above water during construction and/or O&M? e.g. Over water or underwater work, including diving and work in caissons with compressed air supply. Have hazards involved with storm water been considered?
Workplace conditions, extreme temperatures | Does the site involve special work conditions or extreme temperatures? Does the design address the vulnerability to extreme temperatures and provide adequate and appropriate methods to eliminate or reduce those impacts?