## Table 1
|  | Quotation and Detailed Breakdown - Scoping Report - Pump Stations Form | [8 empty] | IDB
Price Schedule
Fee Type: |  |  | Lump Sum Components:
Schedule of Rates Components:
Quotation and Detailed Breakdown
Panel Contract Number: |  |  | Corporation Project Number:
Designer: |  |  | Designer’s Representative:
Design Stage(s): |  |  | Job Title:
Note: Rates and disbursements exclude GST
|  |  | Staff Allocation (Hours) | [6 empty] | Total $ (Excluding GST) | Total $ (Excluding GST) | Comments/Clarification
Job Activity |  |  | Name | Name (Director) | Name (Project Eng) | Name (Senior Eng) | Name (Senior Designer) | Project Secretary | Total Hours
Rate ($)
SCOPING REPORT |  |  | Deliverable
1 | Project Planning
1.1 | Source Planning and Existing Services Data
1.2 | Meetings and Liaison with Water Corporation
1.3 | Local Authority Liaison & in-principle approval
1.4 | Scope, tender, manage & review Survey consultant
1.5 | Scope, tender, manage & review consultants for Geotech
1.6 | Land tenure investigation & resolution
1.7 | Liaison with Environmental Engineer
2 | Preliminary Design Alternatives Review
2.1 | Site Visit / PM Route Walk
2.2 | Complete DAR sheet
2.3 | Assess location for Pump Station
2.4 | Pressure Main Route - (alignments)
2.5 | Overflow to Environment location
2.6 | System Storage and Overflow Storage Calculations
2.7 | Prelim Hydraulic Analysis & Indicative Pump sizing
3 | Site / Route Selection and Preliminary Design & Drawings
3.1 | Concept Layout for Pump Station
3.2 | Pressure Main route (Plan, no long sections) - all alternatives
3.3 | Gravity Sewer Plan
3.4 | Catchment Plan (including HGL calculations)
4 | Scoping Report
4.1 | Prepare and Lodge Scoping Report
4.2 | Updating Scoping Report with WC comments (1 round only)
4.3 | 'Scope of Works' (PTW Plan)
4.4 | Preparation of Opinion of Probable Costs
4.5 | Preparation of Project Environment Data Form (including EATS)
4.6 | Project Program
5 | ESR/Detailed Design Support
5.1 | Allowance for input into Water Corporation ESR/Detailed Design (provisional sum)
Total Hours
Total Labour $ (Excluding GST)
Disbursements $ (Excluding GST)
Total Fee $ (Excluding GST)
6 | Other Consultants for Scoping Report Only (PROVISIONAL AMOUNTS) - Not Covered by Previous Subdivision Investigations
6.1 | Feature & Topo Survey (Pothole Service Locations)
6.2 | Geotechnical Investigation (ASS Investigation & Dewatering)
6.3 | Landscaping Plans/Concepts
6.4 | Environmental Investigations
Total External Consultants Fee $ (Excluding GST)
Approved By: